## WBS
WBS
Item # | Phase - Main Level - Start | Level 1 | Level 2 | Level 3 | Predecessor | Duration | Budget | Notes
|  |  |  | Project Charter Review |  | 1 week
Develop Project Charter
| Wedify | Initiation
|  |  | Hire Project Team |  |  | 2-3 Weeks | 735000 | Meidan Annual Salaries
|  |  |  | Designate Team Roles |  | 3 days
|  |  | Get Stakeholders |  |  | 1 week
|  |  | Scope & Goal Setting |  |  | 3 days
|  | Planning |  | Project Scheduling |  | 1 day
|  |  | Establish Communication Process |  |  | 1-2 days
|  |  | Risk Management |  |  | 1 week
|  |  |  | Risk & EVM Analysis |  | 1 week
|  |  | Budget |  |  | 1 week
|  |  |  | Resource Acquisition |  | 1-2 weeks | 102100 | $72000(OPENAI API) +$100 (App store fee) + $30000 (AWS Services)
1 week
|  |  | Market/User Research |  |  | 1 week
Review Blueprint
|  |  | Create Blueprint |  |  | 2 weeks
|  | UI/UX Design |  | Beta Version
|  |  | Prototyping |  |  | 2 weeks
|  |  |  | Review Userflow |  | 1 week
|  |  | Create Userflow |  |  | 1 week
|  |  |  | Final Design Approval |  | 1 week
|  |  |  | AI Integration |  | 1 month |  | UI/UX design prototyping + Backend & Frontend Dev will be done at the same time. As we have seperate team members that are tasked with certain roles. Which can be completed at the same time.
|  |  |  | Database Development |  | 1 month
Backend Development
|  | Development |  | Module Integration |  | 2 weeks
Frontend Development
|  |  |  | App/Interactivity Functionality |  | 1 month
|  |  |  | Code Review/ Bug Fixing |  | 2 weeks
|  |  | App Testing |  |  | 1 month
Testing/Feedback
|  |  | Integration Testing |  |  | 1 month
|  |  |  | User Feedback |  | 1 week
|  |  | Hire Tester |  |  | 2-3 weeks | 50000 | (500 testers at $100 flat rate)
|  |  |  | Final Launch Approval |  | 1 month
|  |  | App Store Submission |  |  | 1-2 days
|  | Launch |  | Post-Launch Review |  | 2 weeks
|  |  | Marketing/Ad Rollout |  |  | 2 month | 75000 | (marketing overall: social media, tech launch events, etc.) + will be done at after we have completed the blueprint, userflow, & final design approval
|  |  |  | App Maintenance/ 1st app Update |  | 1 month | 10000
1 day
[6 empty] | ~10 Months | 972100 | TOTAL

## PV Planning
WBS Tasks | Week / Month | $$$ | PV | Column B is your schedule, either in weeks or months, depending on your project
| 1 |  |  | List your WBS tasks in the row with the week or month they will be accomplished
| 2 |  |  | Under Column C list the money planned to be spent that week or month on those tasks
| 3 |  |  | Under Column D, build your PV as each planned week or month goes by----
| 4 |  |  | Remember, PV is an accumulating value, each week/month you add more planned spend to it
5
| 6 |  |  | To build your PV chart, 1) select Insert on the menu bar, 2) highlight the data in your Week/Month column, 3) use the Control key to also highlight the data in your PV column, 4)in the Charts section slect the drop down for line graphs, 5) Select a simple line graph, your PV graph should appear. You can change the axis labels, colors, and title.
7
8
9
10