## Sheet1
Risk Register
Number | Risk Description | Risk Category | Impact | Impact Score | Probability Score | Priority Level | Mitigation Plan | Owner
1 | Delays in App Development | Schedule | Launch Delay | 5 | 3 | 15 | Routine App testing, Set constant internal deadlines | Project Manager (overall schedule accountability)
2 | App Store Rejection | Product | Launch Delay | 4 | 2 | 7 | Adhere to app store guidelines, follow privacy terms | Backend Lead / Mobile Lead (compliance + submission process)
3 | Scope Creep (add-ons and categories) | Budget | Cost Overrun | 5 | 1 | 5 | Set firm, frequent milestones. Establish entire scope of project early and adhere to it. | Project Manager (scope control + stakeholder alignment)
4 | Poor Vendor Data | Quality | Lack of Features | 4 | 2 | 8 | Early vendor outreach and partnerships | Marketing Specialist (vendor outreach + partnerships)
5 | Poor user interaction | Product | Lack of Profit | 4 | 3 | 12 | Pre-launch marketing campaigns, sufficient pre-launch beta data collection and improvement | UI/UX Designer (experience)+ Marketing Specialist (user acquisition) (primary: UI/UX)
6 | Copyright Claims from Tinder | Reputation | Launch Delay and/or Product Shutdown | 5 | 1 | 5 | Make original designs and formatting to avoid likeness to Tinder | Project Manager (risk governance) + UI/UX Designer (design differentiation) (primary: PM)
7 | User Privacy Concerns | Reputation | Low app engagement | 3 | 5 | 15 | Build privacy protection into app's architecture | Backend Lead (data security + architecture)
8 | Negative Feedback Loops | Quality | Difficult to grow network | 5 | 3 | 15 | Monitor engagement and feedback closely during testing period | AI/ML Specialist (algorithm tuning) + PM (monitoring) (primary: AI/ML)
9 | Scalability Limitations | Opportunity | Slow Performance | 3 | 3 | 9 | Utilize AWS that support auto-scaling and utilize database supporting scalability | Backend Lead (infrastructure + AWS scaling)