## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ |  |  |  |  | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Wedify |  |  |  |  | COMPANY NAME | [5 empty] | Wedify
PROJECT MANAGER |  | [Richard, Matthew, Patricia, Ines and Julia] |  |  |  |  | DATE | [5 empty] | 2025-10-27
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [11 empty] | PHASE TWO | [11 empty] | PHASE THREE | [11 empty] | PHASE FOUR
[7 empty] | MONTH 1 |  |  |  | MONTH 2 |  |  |  | MONTH 3 |  |  |  | MONTH 4 |  |  |  | MONTH 5 |  |  |  | MONTH 6 |  |  |  | MONTH 7 |  |  |  | MONTH 8 |  |  |  | MONTH 9 |  |  |  | MONTH 10 |  |  |  | MONTH 11 |  |  |  | MONTH 12
[7 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Initiation
1.1 | Project Charter |  | 2025-10-13 | 2025-10-21 | 8 | 100% | bar: MONTH 1 2 to MONTH 1 3; MONTH 2 2
1.1.1 | Project Charter Revisions |  | 2025-10-20 | 2025-10-21 | 1 | 100% | bar: MONTH 1 3; MONTH 2 2
1.2 | Hire Project Manager & Team |  | 2025-10-13 | 2025-10-31 | 18 | 75% | bar: MONTH 1 2 to MONTH 1 4; MONTH 2 2
1.2.1 | Hire PM |  | 2025-10-13 | 2025-10-14 | 1 | 100% | bar: MONTH 1 2; MONTH 2 2
1.2.2 | Designate Team Roles |  | 2025-11-01 | 2025-11-02 | 1 | 50% | bar: MONTH 2 1 to MONTH 2 2
1.3 | WBS |  | 2025-10-14 | 2025-10-21 | 7 | 100% | bar: MONTH 1 2 to MONTH 1 3; MONTH 2 2
1.5 | Stakeholders |  | 2025-11-02 | 2025-11-14 | 12 | 0% | bar: MONTH 2 1 to MONTH 2 2
1.6 | Project Initiation |  | 2025-11-07 | 2025-11-07 | 0 | 0% | bar: MONTH 2 2
2 | Project Planning
2.1 | Scope and Goal Setting |  | 2025-10-14 | 2025-10-21 | 4 | 100% | bar: MONTH 1 2 to MONTH 1 3; MONTH 2 2; MONTH 4 1 to MONTH 4 4
2.1.1 | Project Scheduling |  | 2025-10-14 | 2025-10-21 | 3 | 100% | bar: MONTH 1 2; MONTH 2 2
2.2 | Establish Communication Process |  | 2025-10-14 | 2025-10-21 | 0 | 50% | bar: MONTH 1 2; MONTH 2 2
2.3 | Risk Management |  |  |  |  | 0% | bar: MONTH 1 2; MONTH 2 2
2.3.1 | Risk and EVM Analysis |  | 2025-10-14 | 2026-04-07 |  | 0% | bar: MONTH 1 2 to MONTH 8 1
2.4 | Budget |  |  |  |  | 75% | bar: MONTH 2 2
2.4.1 | Set Budget |  | 2025-11-02 | 2025-11-17 |  | 100% | bar: MONTH 2 1 to MONTH 2 3
2.4.2 | Resource Acquisition |  | 2025-11-05 | 2026-06-02 | 0 | 25% | bar: MONTH 2 2 to MONTH 10 1
3 | UI/UX Design
3.1 | Market/User Research |  | 2025-11-02 | 2025-11-05 | 0 | 0% | bar: MONTH 2 1 to MONTH 2 2
3.2 | Create Blueprint |  | 2025-11-05 | 2025-11-10 | 0 | 0% | bar: MONTH 2 1 to MONTH 2 2
3.2.1 | Review Blueprint |  | 2025-11-10 | 2025-11-12 | 0 | 0% | bar: MONTH 2 2
3.3 | Create Userflow |  | 2025-11-02 | 2025-11-10 | 0 | 0% | bar: MONTH 2 1 to MONTH 2 2
3.3.1 | Review Userflow |  | 2025-11-10 | 2025-11-12 | bar: MONTH 2 2
3.4 | Beta Version |  | 2025-11-12 | 2026-03-28 | 0 | 0% | bar: MONTH 2 2 to MONTH 7 4
3.5 | Final Design Approval |  | 2026-03-28 | 2026-04-01 | 0 | 0% | bar: MONTH 2 2; MONTH 7 4
4 | Development
4.1 | App/Interactivity Functionality |  |  |  | 0 | 0% | bar: MONTH 2 2
4.1.1 | Module Integration |  | 2025-11-12 | 2026-03-01 | 0 | 0% | bar: MONTH 2 2 to MONTH 6 4
4.1.2 | Tinder Swipping Capability |  | 2025-11-12 | 2026-03-01 | 0 | 0% | bar: MONTH 2 2 to MONTH 6 4
4.2 | AI Integration |  |  |  | 0 | 0% | bar: MONTH 2 2
4.2.1 | Use Case Requirements |  | 11/31/25 | 2025-12-03 | 0 | 0% | bar: MONTH 2 2; MONTH 2 4 to MONTH 3 1
4.2.2 | OpenAi API setup |  | 2025-12-03 | 2025-12-10 | 0 | 0% | bar: MONTH 2 2; MONTH 3 1 to MONTH 3 2
4.2.3 | Prompt & Response Design |  | 2025-12-10 | 2025-12-17 | 0 | 0% | bar: MONTH 2 2; MONTH 3 2 to MONTH 3 3
4.2.4 | App Backend Integration |  | 2025-12-17 | 2026-03-01 | 0 | 0% | bar: MONTH 2 2; MONTH 3 3 to MONTH 5 4
4.2.5 | Frontend Integration |  | 2025-12-17 | 2026-03-01 | 0 | 0% | bar: MONTH 2 2; MONTH 3 3 to MONTH 5 4
4.2.6 | Testing/Optimization |  | 2026-03-01 | 2026-03-14 | 0 | 0% | bar: MONTH 2 2; MONTH 5 4 to MONTH 6 2
4.3 | Database Development |  |  |  | 0 | 0% | bar: MONTH 2 2
4.3.1 | Conceptual Design |  | 2025-12-17 | 2025-12-31 | 0 | 0% | bar: MONTH 2 2; MONTH 3 3 to MONTH 3 4
4.3.2 | Logical Design |  | 2025-12-17 | 2025-12-31 | 0 | 0% | bar: MONTH 2 2; MONTH 3 3 to MONTH 3 4
4.3.3 | Physical Design |  | 2025-12-17 | 2025-12-31 | 0 | 0% | bar: MONTH 2 2; MONTH 3 3 to MONTH 3 4
4.3.4 | SQL Implementation |  | 2025-12-31 | 2026-01-15 | 0 | 0% | bar: MONTH 2 2; MONTH 3 4 to MONTH 4 2
4.3.5 | Testing & Validation |  | 2026-01-15 | 2026-02-01 | 0 | 0% | bar: MONTH 2 2; MONTH 4 2 to MONTH 4 4
4.3.6 | Decurity and Backup Setup |  | 2026-02-01 | 2026-02-14 | 0 | 0% | bar: MONTH 2 2; MONTH 4 4 to MONTH 5 2
4.4 | Final Code Review/Bebugging |  | 2026-03-14 | 2026-03-28 | 0 | 0% | bar: MONTH 2 2; MONTH 6 2 to MONTH 6 4
5 | Testing/Feedback
5.1 | Hire Tester |  | 2026-04-01 | 2026-04-07 | 0 | 0% | bar: MONTH 2 2; MONTH 7 1 to MONTH 7 2
5.2 | App Testing |  | 2026-04-03 | 2026-05-01 | 0 | 0% | bar: MONTH 2 2; MONTH 7 1 to MONTH 7 4
5.3 | User Feedback |  |  |  | 0 | 0% | bar: MONTH 2 2
5.3.1 | Create and Launch Survey |  | 2026-03-28 | 2026-04-03 | 0 | 0% | bar: MONTH 2 2; MONTH 6 4 to MONTH 7 1
5.3.2 | Data Collection |  | 2026-04-10 | 2026-05-01 | 0 | 0% | bar: MONTH 2 2; MONTH 7 2 to MONTH 7 4
5.3.3 | Survey Analysis |  | 2026-05-02 | 2026-05-07 | 0 | 0% | bar: MONTH 2 2; MONTH 8 1
5.3.4 | App Refinement |  | 2026-05-07 | 2026-05-28 | 0 | 0% | bar: MONTH 2 2; MONTH 8 2 to MONTH 8 4
5.4 | Final Launch Approval |  | 2026-05-28 | 2026-06-01 | 0 | 0% | bar: MONTH 2 2; MONTH 8 4
6 | Launch
6.1 | App Store Submission |  | 2026-06-01 | 2026-06-03 | 0 | 0% | bar: MONTH 2 2; MONTH 9 1
6.2 | Marketing Rollout |  |  |  | 0 | 0% | bar: MONTH 2 2
6.2.1 | Social Media and Cold Email Campaigns |  | 2026-04-01 | 2026-07-01 | 0 | 0% | bar: MONTH 2 2; MONTH 7 1 to MONTH 9 4
6.2.2 | Tech Launch Event |  | 2026-06-01 | 2026-06-02 | 0 | 0% | bar: MONTH 2 2; MONTH 9 1
6.2.3 | Billboard Ads |  | 2026-06-01 | 2026-07-01 | 0 | 0% | bar: MONTH 2 2; MONTH 9 1 to MONTH 9 4
6.3 | Project/Post-Launch Performance Review |  | 2026-07-02 | 2026-07-07 | 0 | 0% | bar: MONTH 2 2; MONTH 10 1
6.4 | 1st App Update |  |  |  | 0 | 0% | bar: MONTH 2 2
6.4.1 | Analyze App Satisfaction Rates and Comments |  | 2026-07-02 | 2026-07-07 | bar: MONTH 2 2; MONTH 10 1
6.4.2 | Final App Refinement |  | 2026-07-07 | 2026-07-30 | bar: MONTH 2 2; MONTH 10 1 to MONTH 10 4
6.4.3 | App Update Launch |  | 2026-08-01 | 2026-08-01 | bar: MONTH 2 2; MONTH 11 1
6.5 | Project Performance |  | 2026-08-01 |  | 0 | 0% | bar: MONTH 2 2; MONTH 11 1